## Sheet1
Region 9 REI Action Plan 10.22.24
Recommendation 1: Create a region-wide ecosystem steering committee to develop and implement a unified vision for supporting founders and startups across targeted sectors.
Potential partners: | Potential partners in this effort could be representatives from ESOs, economic development, Chambers of Commerce, Venture Central, CBIC, TomTom, SBDC, CIC, Cville Biohub, CVPED, VCW, UVA, Germanna, Laurel Ridge & Piedmont Virginia Community Colleges.
Funding sources: | Go Virginia, Existing ESOs, private foundations, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization to initiate ecosystem steering committee formation | Lead Organization
2025 | Q1 | 1.1 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q1 | 2 | Define the scope and objectives of the steering committee | Lead Organization
2025 | Q2 | 3 | Establish committee structure and recruit members for the Regional Steering Committee | Lead Organization
2025 | Q2 | 4 | Develop a communication plan for regular updates to stakeholders | Regional Steering Committee
2025 | Q3 | 5 | Develop unified regional entrepreneurship vision and strategy | Regional Steering Committee
2026 | Q1 | 6 | Conduct first annual ecosystem health assessment | Regional Steering Committee
2026 | Q3 | 7 | Annual review and strategy refinement - Review and update committee structure and membership | Regional Steering Committee
Recommendation 2: Establish an ecosystem guidance committee in each locality that will guide startup policy and practice.
Potential partners: | Potential partners in this effort could be existing ESOs involved in ecosystem development and interfacing with the Economic Development offices. These may include Venture Central, CBIC, TomTom, SBDC, CIC, Virginia Career Works, Virginia Tourism, college representatives and industry specific entities.
Funding sources: | Go Virginia, Existing ESOs, private foundations, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Conduct initial outreach to local economic development offices | Lead Organization from recommendation #1
2025 | Q1 | 2 | Develop a template for local committee structure and objectives | Lead Organization
2025 | Q1 | 2.1 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q2 | 3 | Identify local leaders and form committees | Local Economic Development Offices
2025 | Q3 | 4 | Develop locality-specific strategic plans aligned with regional goals | Lead Organization with Local Economic Development Offices
2025 | Q3 | 5 | Provide training for newly formed local committees | Lead Organization
2025 | Q4 | 5.1 | Establish regular reporting mechanism between local and regional committees | Lead Organization
2025 | Q4 | 6 | Host informational sessions in each locality about the committee's purpose | Lead Organization
2026 | Q1 | 7 | Facilitate first joint meeting of all local committees | Lead Organization
2026 | Q3 | 8 | Cross-locality collaboration initiative - Host first annual local ecosystem summit | Lead Organization
2027 | Q2 | 9 | Conduct review of local committee effectiveness and adjust as needed | Lead Organization
Recommendation 3: Expand the number of sector specific industry support organizations (peer groups) that will provide mentorship, education, community, and resource exchange.
Potential partners: | Potential partners in this effort could be existing ESOs involved in ecosystem development, event planning, communication, and logistics such as Venture Central, CBIC, TomTom, 434, Chambers of Commerce, SBDC and/or CIC. These organizations could serve as a central support body to help the groups establish their charters and operating procedures, while facilitating information and resource exchange.
Funding sources: | Go Virginia, Existing ESOs, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Conduct research and identify priority sectors for industry support groups | Lead Organization from recommendation #1
2025 | Q1 | 2 | Identify lead ESO to initiate sector specific industry support organizations (could be multiple) | Lead Organization
2025 | Q1 | 3 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q2 | 4 | Evaluate and work to optimize existing groups | Lead Organization
2025 | Q2 | 4.1 | Create gap analysis and develop strategy for new industry support organizations | Lead Organization
2025 | Q4 | 5 | Design structure and funding for new industry support groups | Lead Organization
2026 | Q1 | 6 | Launch first industry support group and establish performance metrics | Lead Organization
2026 | Q3 | 7 | Assess first group's impact and plan for second priority sector | Lead Organization
2026 | Q3 | 8 | Launch second priority sector group and refine first group | Lead Organization
2027 | Q1 | 10 | Conduct comprehensive review and develop sustainability plans | Lead Organization
Recommendation 4: Establish coordinated, sector specific incubators and accelerators that comprise “innovation communities.”
Potential partners: | A lead organization, such as an established Entrepreneur Support Organization (ESO) or economic development entity, can spearhead the effort to develop and launch sector-specific accelerators. This lead organization would then work with industry leaders, higher education partners, investors, community partners, and others.
Funding sources: | Go Virginia, Existing ESOs, VIPC, private funds, federal funds, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization(s) to initiate project | Lead Organization(s)
2025 | Q1 | 2 | Conduct feasibility study for priority sector (e.g., Ag/Food) | Lead Organization(s)
2025 | Q1 | 3 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization(s)
2025 | Q3 | 4 | Develop operational plan for pilot incubator/accelerator | Lead Organization(s)
2025 | Q4 | 5 | Secure funding and partnerships for pilot program | Lead Organization(s)
2026 | Q1 | 6 | Launch pilot incubator/accelerator program | Lead Organization(s)
2026 | Q4 | 7 | Evaluate pilot program and adjust as needed | Lead Organization(s)
2027 | Q1 | 8 | Begin planning for second sector incubator/accelerator | Lead Organization(s)
2028 | Q1 | 9 | Assess regional needs for additional sector programs | Lead Organization(s)
2028 | Q3 | 10 | Launch third sector program based on regional needs (existing item) | Lead Organization(s)
2029 | Q1 | 11 | Conduct comprehensive review of all incubator/accelerator programs | Lead Organization(s)
Recommendation 5: Foster a culture of entrepreneurship and talent retention by creating robust connections between educational institutions, employment resources, and regional businesses.
Potential partners: | Potential partners include a diverse range of educational institutions (high schools, universities, CATECs, and community colleges) alongside entrepreneurship support organizations (ESOs) like CBIC, which bring expertise in startup lifecycles and regional resources.
Funding sources: | Go Virginia, localities, Workforce Boards
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization(s) to initiate project | Lead Organization
2025 | Q1 | 2 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q1 | 3 | Form educational partnership task force with local institutions | Lead Organization
2025 | Q4 | 4 | Assess current entrepreneurship education offerings in the region | Lead Organization
2026 | Q1 | 5 | Create educator training program for entrepreneurship instruction | Lead Organization
2026 | Q2 | 6 | Develop entrepreneurship curriculum for schools | Lead Organization
2026 | Q4 | 7 | Implement entrepreneurship curriculum in pilot schools | Lead Organization
2027 | Q1 | 8 | Evaluate and refine curriculum based on pilot program results | Lead Organization
2027 | Q1 | 9 | Expand curriculum to additional schools and grade levels | Lead Organization
Recommendation 6: Increase the capacity for SBDC, CIC, SCORE, industry focused and other ESOs to support regional businesses.
Potential partners: | Potential partners in this effort could be existing ESOs involved in ecosystem development, event planning, communication, and logistics such as Venture Central, CBIC, SBDC and/or CIC. These organizations could serve as a central support body while local entrepreneurs could take responsibility for setting the agenda for convening.
Funding sources: | Commonwealth of Virginia, localities, other sources needed
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization(s) to initiate project | Lead Organization
2025 | Q1 | 2 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q2 | 3 | Conduct comprehensive assessment of current ESO capacity and needs | Regional Steering Committee
2025 | Q4 | 4 | Assess current ESO capacity and needs | Regional Steering Committee
2025 | Q4 | 5 | Develop strategic plan for ESO capacity enhancement | Regional Steering Committee
2026 | Q2 | 6 | Secure funding and resources for ESO improvements | Lead Organization
2027 | Q1 | 7 | Implement ESO improvement plan | Regional Steering Committee
2028 | Q2 | 8 | Evaluate impact of capacity improvements and adjust as needed | Lead Organization
2029 | Q3 | 9 | Develop long-term sustainability plan for enhanced ESO operations | Lead Organization
Recommendation 7: Widen founder education about and exposure to capital sources and connect more venture capital sources (VCs) with the region.
Potential partners: | Potential partners in this effort could be existing ESOs involved in ecosystem development, event planning, communication, and logistics such as CV SBDC, CIC, Venture Central, 434, banks, and communication and association entities like the Chambers, Cville Biohub, REA, CBIC and TomTom. Local angel groups could help support the effort with content and by supplying speakers and panel members as well as venues and amenities for events.
Funding sources: | Go Virginia, Existing ESOs, Angel Groups, federal funding, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization(s) to initiate project | Lead Organization
2025 | Q1 | 3 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q2 | 2 | Conduct regional capital landscape analysis | Lead Organization
2025 | Q4 | 4 | Organize regional funding education program | Lead Organization
2026 | Q3 | 5 | Develop network of angel investors and VCs interested in the region | Lead Organization
2027 | Q2 | 6 | Host regional investor showcase event | Local Angel Groups
2028 | Q4 | 7 | Establish cross-regional investment network | Lead Organization
Recommendation 8: Provide education and training around the latest technology tools (such as AI, computing technologies, remote workforce management)
Potential partners: | Potential partners in this effort could be: local higher education (e.g., University of Virginia, community colleges), tech companies with a presence in or near the region, local tech meetup groups and organizations (e.g., CBIC), Venture Central, SBDC, and other existing support organizations, and successful tech entrepreneurs from the region who can share real-world insights.
Funding sources: | Go Virginia, Existing ESOs, private company sponsorships, federal funding, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization(s) to initiate project | Lead Organization
2025 | Q1 | 2 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q3 | 3 | Assess regional tech skills gaps and identify priority areas for training | Lead Organization
2026 | Q1 | 4 | Develop tech training curriculum/program (which may include off the shelf programs) | Lead Organization
2026 | Q3 | 5 | Pilot tech training program with select group of entrepreneurs | Lead Organization
2027 | Q2 | 6 | Expand tech training program region-wide | Lead Organization
2028 | Q1 | 7 | Evaluate program effectiveness and update curriculum based on feedback | Lead Organization
2029 | Q2 | 8 | Establish partnerships with tech companies for advanced training opportunities | Lead Organization
Recommendation 9: Craft and amplify a compelling narrative to promote awareness of Central Virginia's entrepreneurial ecosystem within and beyond the region.
Potential partners: | Potential partners in this effort could be the committees described above in Recommendations 1 and 2, as well as existing ESOs involved in ecosystem development, event planning, communication, and logistics. These may include but are not limited to Venture Central, Chambers of Commerce, CBIC, TomTom, SBDC and/or CIC. Such organizations could serve as sources of information and perspective while local entrepreneurs can tell hyper specific stories that can be turned into compelling parts of the overall narrative. VEDP, CVPED and local economic development and tourism offices would also be engaged in these efforts.
Funding sources: | Go Virginia, Existing ESOs, private company sponsorships, local foundations, other community organizations
Action Items:
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2025 | Q1 | 1 | Identify lead organization(s) to initiate project | Lead Organization
2025 | Q1 | 2 | Begin development of a Go Virginia grant application and/or other grant application as applicable | Lead Organization
2025 | Q4 | 3 | Conduct regional brand audit and stakeholder interviews | Lead Organization
2025 | Q4 | 5 | Create regional entrepreneurship success story database | Lead Organization
2026 | Q2 | 4 | Engage marketing firm; Develop communication strategy | Regional Steering Committee
2026 | Q4 | 6 | Launch comprehensive marketing campaign | Marketing firm
2027 | Q4 | 7 | National outreach campaign | Marketing firm
2028 | Q3 | 8 | Evaluate campaign impact and refine long-term communication strategy | Lead Organization
All projects
Year | Quarter | Action item 2 | Action Item | Lead Responsibility
2027 | Q1 |  | Comprehensive two-year impact assessment | Regional Steering Committee
2029 | Q1 |  | Five-year comprehensive review and strategy update | Regional Steering Committee
2025-2030 | All |  | Continue implementation and refinement of programs | Various leads